## Tasks
Project Task Tracker
Days left counts from today, so it is never stale. Use the Status dropdown — the summary counts depend on the exact wording.
Task | Owner | Start | Due | Status | % complete | Days left
Draft project brief | Alex | 2026-08-24 00:47 | 2026-08-31 00:47 | Done | 100%
Stakeholder interviews | Priya | 2026-08-28 00:47 | 2026-09-05 00:47 | Done | 100%
Data model design | Alex | 2026-09-02 00:47 | 2026-09-11 00:47 | In progress | 60%
Build reporting sheet | Sam | 2026-09-07 00:47 | 2026-09-18 00:47 | In progress | 25%
UAT and sign-off | Priya | 2026-09-19 00:47 | 2026-09-26 00:47 | Not started | 0%
Handover documentation | Sam | 2026-09-25 00:47 | 2026-10-02 00:47 | Not started | 0%
Summary
Not started
In progress
Done
Overdue
Average completion
Formulas:
Days left = IF([Status]="Done","—",[Due]-TODAY())